## Sheet1
Work Breakdown and Schedule
Silver Surfer Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
| 1/11 - 1/17 | 1/18 - 1/24 | 1/25 - 1/31 | 2/1 - 2/7 | 2/8 - 2/14 | 2/15 - 2/21 | 2/22 - 2/28 | 2/29 - 3/7 | 3/8 - 3/14 | 3/15 - 3/21 | 3/22 - 3/28 | 3/29 - 4/4 | 4/5 - 4/11 | 4/12 - 4/18 | 4/19 - 4/25 | 4/26 - 5/2
Work Breakdown
Topic Selection | bar: Week 1
SRS Documentation
Rough Draft - Due 1/27 | bar: Week 3
Final Draft - Due 2/8 | bar: Week 5
Press Release
#1 Rough Draft - Due 2/10 | bar: Week 5
#1 Final Draft - Due 2/15 | bar: Week 6
#2 Rough Draft - Due 4/7 | bar: Week 13
#2 Final Draft - Due 4/12 | bar: Week 14
Schedules
Rough Draft - Due 2/10 | bar: Week 5
Final Draft - Due 2/17 | bar: Week 6
Design Documentation
#1 Rough Draft - Due 3/1 | bar: Week 8
#1 Final Draft - Due 3/8 | bar: Week 9
#2 Rough Draft - Due 3/22 | bar: Week 11
#2 Final Draft - Due 3/29 | bar: Week 12
Presentations
Introduction Presentation - Due 2/22 | bar: Week 7
Status Meeting/Presentation - Due 3/31 | bar: Week 12
Final Presentation - Due 4/26 | bar: Week 16
User Manual
Rough Draft - Due 4/14 | bar: Week 14
Final Draft - Due 4/21 | bar: Week 15
Final Report - Due 4/28 | bar: Week 16
Project Goals
Prototyping 2/8 - 2/14 | bar: Week 5
Database Schema 2/15 - 2/21 | bar: Week 6
Building Pages 2/15 - 3-7 | bar: Week 6 to Week 8
Creating Dynamic Routing for Pages 2-22 - 2/28 | bar: Week 7
Building Components (Ongoing) (2/15 - 4/4) | bar: Week 6 to Week 12
Adding Components (Ongoing) 3/22 - 4/18 | bar: Week 11 to Week 14
Designing API 3/7 - 3/14 | bar: Week 8 to Week 9
Login Authentication 2/22 - 3/7 | bar: Week 7 to Week 8
Layout for creating/editing pages 2/22 - 3/7 | bar: Week 7 to Week 8
Admin Panel for adding/editing pages 3/22 - 4/11 | bar: Week 11 to Week 13
Phase 1 Testing 3/8 - 3/14 | bar: Week 9
Basic Web Page Development 3/8 - 4-11 | bar: Week 9 to Week 13
Phase 2 Testing 3/29 - 4/4 | bar: Week 12
Aesthetic Improvements 4/5 - 4/18 | bar: Week 13 to Week 14
Final Phase of Testing 4/19 - 4/25 | bar: Week 15
Legend
Due Dates for course objectives
Project Objectives and Weekly Goals
Final Project Due